## Sheet1
Defect ID | Module Name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review Type/ Test Cycle | Test Case ID | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachments | Comments
DF_001 | Login | After entering valid userID and password User is unable to login. | Detailed Description: On clicking login button and entering Valid userID and Password user is unable to navigate to next prespective page of the application and hence login fails. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on login' text link 4.Enter valid userID and password 5.Click on login Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to login the user on next web page as expected. The application stays on the same page and user is not logged in. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.1 | 3 | 29/11/2018 | Naman Awasthi | Rutuja | ACT |  | TC_SIGNIN_002
DF_002 | Book Flight | Due to unsuccessfull Payment user is unable is Book Flight . | Detailed Description: The user is unable to Book Flight as he/she is unable to make successfull payment even after emtering correct credentails Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on login' text link 4.Enter valid userID and password 5.Click on login Button 6.click on find flight 7.select flight and click on book flight to make payment. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to book flight for user even after entering valid credentials not working as expected. The application displays error message. | Coding | Internet Explorer | External Dev | P3 | Medium | 1.3.2 | 4 | 29/11/2018 | Naman Awasthi | Rutuja | REOPENED |  | TC_BOOK_FLIGHT_004
DF_003 | Itinerary | The user is unable to cancil flight once it is booked | Detailed Description: The user clicks on itinerary . The cancil flight option is found but unable to cancil user flight Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on login' text link 4.Enter valid userID and password 5.Click on login Button 6.Click on itinerary text link 7.Click on cancil flight button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the cancil flight feild of an application is unable to cancil user flight as expected by tester. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.3 | 5 | 29/11/2018 | Naman Awasthi | Rutuja | ACT |  | TC_ITINERARY_006
DF_001 | Tour_page_secure | The webpage is found unable to display error message(Please enter a 10 digit mobile number) by accepting invalid password | Detailed Description: The webpage is found unable to display error message("Please Enter 10 digit mobile number") by accepting invalid mobile No Steps To reproduce the bug: 1.Enter URL https://newtours.demorout.com 2.after entering credential Click on registration button 3.after entering flights details click on secure purchase button. 4.Enter the data in mobile no field. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the The Mobile No Field is Accepting the invalid data as expected. Error message is not displaying | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 2018-11-02 | Mayur more | Naman Avasthi | ACT |  | TC_002
DF_002 | Tour_page_secure | The website is found unable to send otp even after entering valid mobile number | Detailed Description: The website is found unable to send otp even after entering valid mobile number Steps To reproduce the bug: 1.Enter URL https://newtours.demorout.com 2.after entering credential Click on registration button 3.after entering flights details click on secure purchase button. 4.Enter the valid data in mobile no field. 5.Click on "Send OTP" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Webpage is not sending an OTP even after entering the valid mobile no. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 | 2018-11-02 | Mayur more | Naman Avasthi | ACT |  | TC_003
DF_003 | Tour_page_secure | The webpage is found unable to display error message(Please enter a 6 digit OTP) by accepting invalid OTP which is greater than 6 | Detailed Description: The webpage is found unable to display error message(Please enter a 6 digit OTP) by accepting invalid OTP which is greater than 6 Steps To reproduce the bug: 1.Enter URL https://newtours.demorout.com 2.after entering credential Click on registration button 3.after entering flights details click on secure purchase button. 4.Enter the valid data in mobile no field. 5.Click on "Send OTP" button 6.Enter an invalid data in OTP No field Actual result observed on running above steps: On executing the above mentioned steps it is observed that the The OTP Field is Accepting the invalid data as expected. Error message is not displaying | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 2018-11-02 | Mayur more | Naman Avasthi | ACT |  | TC_002
DF_004 | Tour_page_secure | The webpage is found unable to display error message(Please enter a 6 digit OTP) by accepting invalid OTP which is less than 6 | Detailed Description: The webpage is found unable to display error message(Please enter a 6 digit OTP) by accepting invalid OTP which is less than 6 Steps To reproduce the bug: 1.Enter URL https://newtours.demorout.com 2.after entering credential Click on registration button 3.after entering flights details click on secure purchase button. 4.Enter the valid data in mobile no field. 5.Click on "Send OTP" button 6.Enter an invalid data in OTP No field Actual result observed on running above steps: On executing the above mentioned steps it is observed that the The OTP Field is Accepting the invalid data as expected. Error message is not displaying | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 2018-11-02 | Mayur more | Naman Avasthi | ACT |  | TC_002
DF_005 | Tour_page_secure | After clicking '"Verify' button it is found unable to navigate to Flight Confirmation page. | Detailed Description: After clicking '"Verify' button it is found unable to navigate to Flight Confirmation page. Steps To reproduce the bug: 1.Enter URL https://newtours.demorout.com 2.after entering credential Click on registration button 3.after entering flights details click on secure purchase button. 4.Enter the valid data in mobile no field. 5.Click on "Send OTP" button 6.Enter an valid data in OTP No field 7.Click on "Verify" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is not redirecting to the Flight Confirmation Page, as expected. The application stays on the same page. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.1 | 3 |  | Mayur more | Naman Avasthi |  |  | Tc_002
DF_001 | FlighT | The Flight tab is found to be unable to navigate user to Flight page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Flight" page by clicking on "Flight" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Flight" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Flight page as expected. | Coding | Internet Explorer | Internal Dev | P2 | Medium | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_002
DF_002 | Register | The "Register " tab is found to be unable to navigate user to Register page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_003
DF_003 | SignOn | The "Sign On" tab is found to be unable to navigate user to Register page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_004
DF_004 | Cruise_Special | The "Cruise Special" tab is found to be unable to navigate user to "Cruise Special" page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P3 | Low | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_007