## Sheet1
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_001 | User_Reg_link | The application is found unable to redirect to the registration page of the application on clicking of 'Lets Get Started' tab. | Detailed Description: The application is found unable to redirect to the registration page of the application on clicking of 'Lets Get Started' tab. Steps To reproduce the bug: 1. Open Browser 2.1.Enter the URL www.magentomobileshop.com in the addressbar. 3.Click on the 'Let's Get Started' tab. Actual result observerd on running above steps: On executing the above steps it is observerd that application is unable to redirect the user to the registration page as expected. The application is displaying the same page. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 3 |  | Shweta Pawar
DF_002 | User_Reg_Name | The application is found unable to display the error message as 'please enter valid name' after entering invalid username. | Detailed Description: The application is found unable to display the error message as 'please enter valid name' after entering invalid username. Steps To reproduce the bug: 1. Open Browser 2.1.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the invalid username. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to display the error mesage, as expected. The username field of Application is accepting the invalid username. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 3 |  | Shweta Pawar |  |  |  | TC_003
DF_003 | User_Reg_Name | The application is found unable to display the error message as 'please fill out this field' after leaving the username field blank. | Detailed Description: The application is found unable to display the error message as 'please fill out this field' leaving the username field blank. Steps To reproduce the bug: 1. Open Browser 2.1.Enter the URL www.magentomobileshop.com in the addressbar. 3.Keep the username field blank. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to display the error mesage, as expected. The username field of application is accepting the null value. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 4 |  | Shweta Pawar |  |  |  | TC_004
DF_004 | User_Reg_Email | The application is found unable to display the error message as 'please enter valid email' after entering invalid email address. | Detailed Description: The application is found unable to display the error message as 'please enter valid email' after entering invalid email address. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4. Click on Email and Enter the invalid Email ID Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Email Field is not accepting the email address as expected. The email field of an application is accepting the invalid email address. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar |  |  |  | TC_007
DF_005 | User_Reg_Email | The application is found unable to accept the email address after entering the valid data. | Detailed Description: The application is found unable to accept the email address after entering the valid data. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4. Click on Email and Enter the valid Email ID Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Email Field is not accepting the email ID as expected. The email field of an application is not accepting the valid email address. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar
DF_006 | User_Reg_Email | The application is found unable to display the error message as 'Please fill out this field' after leaving the email address field blank. | Detailed Description: The application is found unable to display the error message as 'Please fill out this field' after leaving the email address field blank. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4. Keep the email address field blank. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Email Field is not accepting the email ID as expected. The email field of an application is accepting the null value. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar
DF_007 | User_Reg_Password | The application is found unable to display the error message as 'please enter valid password' after entering invalid password. | Detailed Description: The application is found unable to display the error message as 'Please enter valid password' after entering the invalid password. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4. Enter the email address. 5.Enter the invalid password. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Password Field is not accepting the password as expected. The password field of an application is accepting the invalid password. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar |  |  |  | TC_010
DF_008 | User_Reg_Password | The application is found unable to display the error message as 'please fill out this field' after leaving the password field blank. | Detailed Description: The application is found unable to display the error message as 'Please fill out this field' after leaving the password field blank. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4.Enter the email address. 5.Keep the password field blank. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Password Field is not accepting the password as expected. The password field of an application is accepting the null value. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar |  |  |  | TC_011
DF_009 | User_Reg_Submit | The application is found unable to redirect to the desired page after clicking on the submit button. | Detailed Description: The application is found unable to redirect to the desired page after clicking on the submit button. Steps To reproduce the bug: 1. Open Browser 2.Enter the URL www.magentomobileshop.com in the addressbar. 3.Enter the user name. 4.Enter the Email address. 5.Enter the password. 6.Click on the button 'Get Started'. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the submit button is not navigating to desired page as expected. The Application is displaying the same page. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 |  | Shweta Pawar |  |  |  | TC_012
Note on A1: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B1: Alphy Chenganiyadan: Give the name of the module being tested
Note on C1: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D1: Alphy Chenganiyadan: A detailed description of the defect
Note on E1: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F1: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G1: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H1: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I1: Prioritize the defect
Note on J1: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K1: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L1: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M1: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N1: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O1: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P1: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q1: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on S1: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T1: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U1: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V1: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W1: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X1: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y1: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.